## Лист1
Timescale |  | ITERATION STATUS
|  | ID |  | Name | Schedule state (D, P, C, A) | Task Est | To Do | Actuals
5.09.18 | 11.09.18 |  |  |  |  | 28
|  | US1 |  | Investigate and install frameworks and Microsoft SQL | P | 28 | 20 | 8
|  |  | TA1 | Planning | P | 8 | 4 | 4 | D
|  |  | TA2 | Investigate React, Redux | P | 4 | 2 | 2 | P
|  |  | TA3 | Investigate .Net Rest Api | P | 4 | 2 | 2 | C
|  |  | TA4 | Install the necessay frameworks and libraries | C | 8 | 8 | 0 | A
|  |  | TA5 | Install Microsoft SQL Server and SQL Server Management Studio | C | 4 | 4 | 0
12.09.18 | 18.09.18 |  |  |  |  | 36
|  | US2 |  | Investigate and install frameworks and Microsoft SQL | C | 12 | 21 | 15
|  |  | TA6 | Planning | C | 4 | 4 | 0
|  |  | TA7 | Investigate React, Redux | C | 4 | 4 | 0
|  |  | TA8 | Investigate .Net Rest Api | C | 4 | 4 | 0
|  | US3 |  | Database | P | 16 | 5 | 11
|  |  | TA9 | Structure of database (entities and relationships) | P | 8 | 4 | 4
|  |  | TA10 | Add the database in Microsoft SQL | P | 8 | 1 | 7
|  | US4 |  | Backend Web Api (app with GET method) | D | 8 | 0 | 8
|  |  | TA11 | Create .Net Rest Api application with GET method | D | 4 | 0 | 4
|  |  | TA12 | Connect App with Microsoft SQL (EntityF.) | D | 4 | 0 | 4
19.09.18 | 25.09.18 |  |  |  |  | 40
|  | US5 |  | Backend Web Api (add POST, PUT, DELETE methods) | D | 40 | 0 | 40
|  |  | TA13 | Add POST method (controllers+services+DAL) | D | 4 | 0 | 4
|  |  | TA14 | Add PUT method (controllers+services+DAL) | D | 4 | 0 | 4
|  |  | TA15 | Add DELETE method (controllers+services+DAL) | D | 4 | 0 | 4
|  |  | TA16 | Testcases | D | 4 | 0 | 4
|  |  | TA17 | Unit tests | D | 12 | 0 | 12
|  |  | TA18 | Integration tests | D | 8 | 0 | 8
|  |  | TA19 | Testing | D | 4 | 0 | 4
26.09.18 | 2.10.18 |  |  |  |  | 0
3.10.18 | 9.10.18 | US6 |  | Frontend React/Redux | D | 0 | 0 | 0
10.10.18 | 16.10.18
17.10.18 | 23.10.18 |  |  |  |  | 0
|  | US7 |  | E2E Regression | D | 0 | 0 | 0
24.10.18 | 30.10.18