## Лист1
|  | ID |  | Name | Schedule state (D, P, C, A) | Task Est | To Do | Time Spent
5.09.18 | 11.09.18 |  |  |  |  | 28
|  | US1 |  | Investigate and install frameworks and Microsoft SQL | P | 28 | 20 | 8
|  |  | TA1 | Planning | P | 8 | 4 | 4 |  | D
|  |  | TA2 | Investigate React, Redux | P | 4 | 2 | 2 |  | P
|  |  | TA3 | Investigate .Net Rest Api | P | 4 | 2 | 2 |  | C
|  |  | TA4 | Install the necessay frameworks and libraries | C | 8 | 8 | 0 |  | A
|  |  | TA5 | Install Microsoft SQL Server and SQL Server Management Studio | C | 4 | 4 | 0
12.09.18 | 18.09.18 |  |  |  |  | 38
|  | US2 |  | Investigate and install frameworks and Microsoft SQL | C | 12 | 36 | 0
|  |  | TA6 | Planning | C | 4 | 4 | 0
|  |  | TA7 | Investigate React, Redux | C | 4 | 4 | 0
|  |  | TA8 | Investigate .Net Rest Api | C | 4 | 4 | 0
|  | US3 |  | Database | C | 16 | 16 | 0
|  |  | TA9 | Structure of database (entities and relationships) | C | 8 | 8 | 0
|  |  | TA10 | Add the database in Microsoft SQL | C | 8 | 8 | 0
|  | US4 |  | Backend Web Api (app with GET method) | P | 10 | 3 | 7
|  |  | TA11 | Investigate OData | C | 2 | 2 | 0
|  |  | TA12 | Create .Net Rest Api application with GET method (controllers+services+DAL) | P | 4 | 1 | 3
|  |  | TA13 | Connect App with Microsoft SQL (EntityF.) | D | 4 | 0 | 4
19.09.18 | 25.09.18 |  |  |  |  | 76
|  | US5 |  | Update database | C | 6 | 3.25 | 2.75
|  |  | TA14 | Update structure of database to minimal project | C | 2 | 1 | 1
|  |  | TA15 | Create new database in Microsoft SQL | C | 2 | 1 | 1
|  |  | TA16 | Update database | C | 1 | 1 | 0
|  |  | TA17 | Update database in SQL Server | C | 1 | 0.25 | 0.75
|  | US6 |  | Backend Web Api (add GET, POST methods) | P | 46 | 1 | 59
|  |  | TA18 | Create .Net Rest Api application | C | 2 | 2 | 0
|  |  | TA19 | Connect App with Microsoft SQL (EntityF.) | C | 4 | 4 | 4
|  |  | TA20 | Add GET method for "List of products" (controllers+services+server side validation+DAL) | C | 4 | 16 | -12 | Controllers: Products, Users, Orders, ItemsOfOrders Method GET: Products, Users, Orders, ItemsOfOrders
|  |  | TA21 | Add POST method for "Create order" (controllers+services+server side validation+DAL) | C | 8 | 2 | 6 | Method POST: Products, Users, Orders, ItemsOfOrders
|  |  | TA22 | Testcases | D | 4 | 0 | 4
|  |  | TA23 | Unit tests | D | 12 | 0 | 12
|  |  | TA24 | Integration tests | D | 8 | 0 | 8
|  |  | TA25 | Testing | D | 4 | 0 | 4
|  | US7 |  | Mock-ups for List of products and Orders | C | 4 | 1 | 3
|  |  | TA26 | Create mock-up for page with List of products | C | 2 | 0.5 | 1.5
|  |  | TA27 | Create mock-up for page with Order | C | 2 | 0.5 | 1.5
|  | US8 |  | Frontend React/Redux | D | 20 | 0 | 20
|  |  | TA29 | Create SPA with simple components for List of product | D | 8 | 0 | 8
|  |  | TA30 | Create SPA with simple components for Cart | D | 8 | 0 | 8
|  |  | TA28 | Connect App with React/Redux infrastructure | D | 4 | 0 | 4
26.09.18 | 2.10.18 |  |  |  |  | 48.5 | 43
|  | US9 |  | [Continue] Backend Web Api | D | 8 | 0 | 8
|  |  | TA32 | Add logic for the situation when items are added to a non-existent order | D | 8 | 0 | 8
|  | US10 |  | [Continue] Frontend React/Redux | P | 40.5 | 37.5 | 3
|  |  | TA33 | Create SPA with simple components for List of product | C | 8 | 8 | 0
|  |  | TA34 | Create SPA with simple components for Cart | C | 8 | 8 | 0
|  |  | TA35 | Connect App with React/Redux infrastructure | C | 4 | 4 | 0
|  |  | TA36 | Functionality "add to cart/remove from cart" | P | 4 | 5 | -1
|  |  | TA37 | Functionality "create items" | P | 4 | 2 | 2
|  |  | TA38 | Functionality "create order" | D | 4 | 0 | 4
|  |  |  | Defects | C | 4.5 | 5.5 | -1
|  |  | D1 | Fix path to js/main.*.js in ReactReduxApp and connect with IIS | C | 4 | 5 | -1
|  |  | D2 | Merge DB context files into one file | C | 0.5 | 0.5 | 0
3.10.18 | 9.10.18 |  |  |  |  | 61 | 60
|  | US11 |  | [Continue] Backend Web Api | D | 44 | 54 | 180
|  |  | TA39 | Add services+server side validation for all models | D | 8 | 0 | 8
|  |  | TA40 | Testcases | D | 4 | 0 | 4
|  |  | TA41 | Unit tests | D | 12 | 0 | 12
|  |  | TA42 | Integration tests | D | 8 | 0 | 8
|  |  | TA43 | Testing | D | 4 | 0 | 4
|  | NN | TA44 | Add logic for the situation when items are added to a non-existent order | D | 8 | 0 | 8
|  | US12 |  | [Continue] Frontend React/Redux | C | 8 | 6 | 2
|  |  | TA45 | Functionality "create items" | C | 4 | 4 | 0
|  |  | TA46 | Functionality "create order" | C | 4 | 2 | 2
|  |  |  | Defects | P | 9 | 8 | 1
|  |  | D1 | Fix re render of tab "Cart" | C | 4 | 8 | -4
|  |  | D2 | Security Issue | D | 5 | 0 | 5
|  | US13 |  | Frontend html/css | P | 24 | 13 | 24
|  |  | TA47 | Create UI for App component | P | 8 | 8 | 8
|  |  | TA48 | Create UI for Products component | P | 8 | 5 | 8
|  |  | TA49 | Create UI for Cart component | D | 8 | 0 | 8
10.10.18 | 16.10.18 |  |  |  |  | 36 | 0
|  | US14 |  | [Continue] Backend Web Api | D | 36 | 0 | 36
|  |  | TA50 | Add services+server side validation for all models | D | 8 | 0 | 8
|  |  | TA51 | Testcases | D | 4 | 0 | 4
|  |  | TA52 | Unit tests | D | 12 | 0 | 12
|  |  | TA53 | Integration tests | D | 8 | 0 | 8
|  |  | TA54 | Testing | D | 4 | 0 | 4
|  |  |  | Defects | D | 5 | 0 | 5
|  |  | D1 | Security Issue | D | 5 | 0 | 5 | 1 action
|  | US13 |  | [Continue] Frontend html/css | D | 0 | 0 | 0
|  |  | TA55 | Create UI for App component | D | 0 | 0 | 0
17.10.18 | 23.10.18 |  |  |  |  | 80
|  | US8 |  | E2E Regression | D | 0 | 0 | 0
24.10.18 | 30.10.18